## Sheet1
Risks | Risk Theme | Category | Risk_Categories | Region | Hospital Type | Project Type | Context Tags | Infrastructure Level | Investment Level | Lifecycle phase classification | Lifecycle Phase
PMO unavailability | Project Management & Governance Failures | Governance | Project management; Organisation | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | PMO maturity gap | Low | High | Initiation | Initiation
Change management weaknesses | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; People | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Resistance to change | Low | High | Deployment/Go-live | Deployment
Unclear requirements & scope | Workflow & Process Misalignment | Workflow/Process | Process; Requirements | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Scope definition, requirements volatility | High | High | Planning/Design | Planning/Design
Undefined risks | Project Management & Governance Failures | Governance | Project management (Risk) | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Missing risk register | High | High | Planning (Risk) | Planning/Design
Undefined stakeholders | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Stakeholder mapping absent | High | High | Initiation | Initiation
Poor communication | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; People | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Escalation gaps | High | High | Execution | Execution
Poor project planning | Project Management & Governance Failures | Governance | Project management (Time/Scope/Cost) | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Scheduling, WBS quality | Low | High | Planning | Planning/Design
Project execution issues | Project Management & Governance Failures | Workflow/Process | Process; Quality | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Delivery slippage, defects | Low | High | Execution | Execution
Poor resource management | Project Management & Governance Failures | Human Factors | Resource; HR | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Understaffing, skill mix | Low | High | Planning/Execution | Execution
Poor people management (e.g., suppliers) | Stakeholder, Leadership & Cultural Issues | Governance | Vendor/Procurement; HR | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Supplier oversight, contracts | Low | High | Procurement/Execution | Execution
Lack of training | Human Resources, Training & User Support | Human Factors | Training; End-user | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | User readiness | Low | High | Deployment/Stabilisation | Deployment
Lack of vendor support | Vendor & External Dependence | Governance | Vendor/Support | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | SLA, post-go-live help | Low | High | Operations/Maintenance | Operations
Lack of user support | Human Resources, Training & User Support | Human Factors | Support; Adoption | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Helpdesk, champions | Low | High | Operations/Maintenance | Operations
Poor consultant competence | Human Resources, Training & User Support | Human Factors | Consultancy; Skills | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | External expertise gaps | Low | High | Design/Configuration | Planning/Design
Inadequate system selection | Technical System & Infrastructure Failures | Governance | Technical; Procurement | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Fit-for-purpose, COTS mismatch | Low | High | Initiation/Procurement | Initiation
Low quality of service (QoS) | Technical System & Infrastructure Failures | Technical | Service Quality; Technical | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Availability, performance | Low | High | Operations | Operations
Low computing literacy | Technical System & Infrastructure Failures | Human Factors | People; Training | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Digital skills gap | Low | High | Training/Deployment | Deployment
Poor infrastructure | Technical System & Infrastructure Failures | Technical | Infrastructure | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Network, hardware limits | Low | High | Operations/Deployment | Deployment
Security, privacy, trust issues | Technical System & Infrastructure Failures | Security/Privacy | Cybersecurity/Privacy | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Data protection, trust | Low | High | Design/Operations | Operations
Poor leadership | Stakeholder, Leadership & Cultural Issues | Governance | Leadership; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Decision latency | Low | High | Initiation/Execution | Execution
Organisational culture barriers | Stakeholder, Leadership & Cultural Issues | Human Factors | Culture; Organisation | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Centralisation, autocracy | Low | High | All phases (primarily Planning/Execution) | Cross-phase
Conflict of interest | Stakeholder, Leadership & Cultural Issues | Ethical/Legal | Governance; Ethics | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Vendor influence, bias | Low | High | Procurement/Execution | Execution
Low citizen/public trust | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder; External | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Public-facing systems | Low | High | Deployment/Operations | Deployment
Lack of top management support | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Leadership | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Executive sponsorship | Low | High | Initiation/Planning | Initiation
Top management instability | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Organisation | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Leadership turnover | Low | High | Initiation/Execution | Execution
Legal & regulatory issues | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory/Legal | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Compliance gaps | Low | High | Design/Procurement | Planning/Design
Lack of cooperation/collaboration | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; Organisation | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Inter-dept silos | Low | High | Execution | Execution
Business process reengineering (BPR) challenges | Workflow & Process Misalignment | Human Factors | Process; Change management | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | Misfit with workflows | Low | High | Design/Configuration | Planning/Design
Financial factors low salience due to subsidisation (context) | Organisational Performance & Benefits Realisation | Financial | Financial (context) | Saudi Arabia | Tertiary / Teaching Hospitals | IT software projects | High government funding reduces finance-driven failures | High | High | Cross-phase context | Cross-phase
Design–reality gaps | Project Management & Governance Failures | Governance | Process; Governance | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Misalignment between design and operational reality; underestimated user volume | High | High | Planning/Execution | Execution
Missing focus | Project Management & Governance Failures | Governance | Governance; Strategic | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Unclear objectives, absence of need | High | High | Initiation/Planning | Initiation
Content issues | Risk Framework & Analytical Weaknesses | Technical | Process; Technical | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Scope changes, shifting requirements, technical complexity | High | High | Design/Configuration | Planning/Design
Skill issues | Human Resources, Training & User Support | Human Factors | People; HR | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Lack of aligned skills, overreliance on external contractors | High | High | Planning/Execution | Execution
Execution issues | Project Management & Governance Failures | Governance | Project management; Process | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Unrealistic scheduling, reactive planning, cost overruns | High | High | Execution | Execution
Regulatory issues | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory/Legal | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Legal framework gaps, unpredictable policy changes | High | High | Planning | Planning/Design
External factors | Vendor & External Dependence | Governance | External | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Political pressure, media scrutiny | High | High | Execution | Execution
Missing user satisfaction | Organisational Performance & Benefits Realisation | Human Factors | Stakeholder; Adoption | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Public dissatisfaction, low adoption | High | High | Operations/Maintenance | Operations
Organisational power issues | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Organisation | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Complex stakeholder network | High | High | Initiation/Execution | Execution
Political overestimation | Stakeholder, Leadership & Cultural Issues | Governance | Governance; External | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Political will assumed to ensure success | High | High | Initiation | Initiation
Education/training gaps | Human Resources, Training & User Support | Human Factors | Training; People | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Insufficient training for system operation | High | High | Deployment/Stabilisation | Deployment
Project management issues | Project Management & Governance Failures | Governance | Project management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Weak requirement definition, risk mismanagement | High | High | Planning/Execution | Execution
Ambiguous business needs/vision | Project Management & Governance Failures | Governance | Governance; Strategy | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Lack of clear mission alignment | High | High | Initiation | Initiation
ICT/system development process issues | Workflow & Process Misalignment | Technical | Technical; Infrastructure | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Inadequate architecture, integration issues | High | High | Design/Execution | Execution
Overreliance on contractors | Vendor & External Dependence | Governance | Vendor/Procurement | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | 55+ contractors; fragmented accountability | High | High | Procurement/Execution | Execution
Evolving requirements | Workflow & Process Misalignment | Workflow/Process | Process; Requirements | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Requirements instability | High | High | Planning/Design | Planning/Design
Non-sequential development/testing | Workflow & Process Misalignment | Workflow/Process | Process; Quality | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Build-test overlap reduced QA | High | High | Execution | Execution
Lack of cost control | Project Management & Governance Failures | Financial | Financial; Project management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | $630M spend without clear budget tracking | High | High | Planning/Execution | Execution
Unrealistic requirements engineering | Workflow & Process Misalignment | Workflow/Process | Requirements; Quality | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Complexity underestimated | High | High | Planning | Planning/Design
Ambiguous HR arrangements | Stakeholder, Leadership & Cultural Issues | Governance | HR; Vendor | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Contractor-heavy staffing | High | High | Procurement/Execution | Execution
Complex communications | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; Stakeholder | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Poor stakeholder alignment | High | High | Planning/Execution | Execution
Insufficient risk management | Project Management & Governance Failures | Governance | Risk management; Project management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Failure to anticipate scale/load issues | High | High | Planning | Planning/Design
Complex procurement | Vendor & External Dependence | Governance | Procurement; Governance | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Multi-vendor contracting complexity | High | High | Procurement | Procurement
Stakeholder overload | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Many agencies, states, insurers involved | High | High | Initiation/Execution | Execution
Inadequate testing before launch | Testing, Quality & Evaluation Gaps | Workflow/Process | Quality; Process | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Testing done only 2 weeks before launch | High | High | Testing/Deployment | Deployment
System architecture unable to handle load | Technical System & Infrastructure Failures | Technical | Technical; Infrastructure | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Load capacity underestimated | High | High | Design/Execution | Execution
Single point of failure in hosting | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Data center outage halted enrolment | High | High | Operations/Maintenance | Operations
Delayed recognition of problems | Testing, Quality & Evaluation Gaps | Governance | Communication; Project management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Key leadership unaware until after launch | High | High | Execution | Execution
Shifting scope before launch | Project Management & Governance Failures | Human Factors | Process; Change management | USA | Tertiary / Teaching Hospitals | National EHR/insurance exchange platform | Add-ons just before launch blocked testing | High | High | Design/Testing | Planning/Design
Increased clinician workload & workflow disruption | Workflow & Process Misalignment | Workflow/Process | Usability; Workflow; People | USA | Tertiary / Teaching Hospitals | EHR Implementation | Clinician burden; Task switching; Documentation inefficiency | High | High | Operations/After implementation | Operations
Mixed outcomes on clinical quality benefits | Organisational Performance & Benefits Realisation | Workflow/Process | Clinical Safety; Quality | USA | Tertiary / Teaching Hospitals | EHR Implementation | Variable quality improvements | High | High | Operations | Operations
Financial/cost implications not always positive | Organisational Performance & Benefits Realisation | Financial | Financial; Strategy | USA | Tertiary / Teaching Hospitals | EHR Implementation | High initial cost; ROI uncertainty | High | High | Planning/ Implementation | Planning/Design
Barriers: poor training, technical support, literacy | Human Resources, Training & User Support | Human Factors | Training; Technical | USA | Tertiary / Teaching Hospitals | EHR Implementation | Education gap; IT support weak | High | High | Deployment/Stabilisation | Deployment
Adoption influenced by policy incentives | Vendor & External Dependence | Governance | Governance; External | USA | Tertiary / Teaching Hospitals | EHR Implementation | Meaningful Use incentives | High | High | Initiation/Planning | Initiation
Variation in realized benefits across settings | Organisational Performance & Benefits Realisation | Ethical/Legal | Contextual; Equity | USA | Tertiary / Teaching Hospitals | EHR Implementation | Implementation level differences | High | High | Operations | Operations
Lack of comprehensive, systematic approach in dashboard development | Risk Framework & Analytical Weaknesses | Workflow/Process | Process; Methodology | Global/International | Tertiary / Teaching Hospitals | Healthcare Dashboard Development | Absence of unified development standards | Low | High | Initiation/Planning | Initiation
Gaps in methods and frameworks comparison | Risk Framework & Analytical Weaknesses | Workflow/Process | Methodology; Research | Global/International | Tertiary / Teaching Hospitals | Healthcare Dashboard Development | Need for comparative evaluation studies | Low | High | Optimisation | Post-implementation
Development goals and metrics not always aligned to healthcare unit needs | Risk Framework & Analytical Weaknesses | Governance | Governance; Process | Global/International | Tertiary / Teaching Hospitals | Healthcare Dashboard Development | Misaligned KPIs, unit-specific relevance | Low | High | Planning/Design | Planning/Design
Technical and integration challenges across diverse healthcare systems | Technical System & Infrastructure Failures | Technical | Technical; Interoperability | Global/International | Tertiary / Teaching Hospitals | Healthcare Dashboard Development | Data integration complexity | Low | High | Design/Implementation | Implementation
Limited adoption due to usability or training gaps | Human Resources, Training & User Support | Human Factors | Usability; Training | Global/International | Tertiary / Teaching Hospitals | Healthcare Dashboard Development | End-user adoption barriers | Low | High | Deployment/Stabilisation | Deployment
Complex organisational structures (gov, software, local orgs) cause errors | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Socio-technical | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Multi-layer org complexity | Low | High | Planning/Initiation | Initiation
Errors from design and development of technology | Technical System & Infrastructure Failures | Technical | Technical; Process | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Poor design/development | Low | High | Design/Development | Planning/Design
Errors from implementation and customisation | Technical System & Infrastructure Failures | Technical | Process; Configuration | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Risk during customisation | Low | High | Implementation | Implementation
Interaction between technology operation and new workflows | Workflow & Process Misalignment | Workflow/Process | Process; Workflow | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Workflow-tech misalignment | Low | High | Operations | Operations
Unintended consequences (e-iatrogenesis) as error sources | Technical System & Infrastructure Failures | Workflow/Process | Clinical Safety; Unintended Consequences | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Unexpected systemic effects | Low | High | Operations | Operations
Undetected errors due to human/usability interface flaws | Human Resources, Training & User Support | Workflow/Process | Usability; Human Factors | Canada | Tertiary / Teaching Hospitals | HIS Implementation | UI usability-induced errors | Low | High | Testing/Deployment | Deployment
Ethnographic and observer bias hide errors | Risk Framework & Analytical Weaknesses | Human Factors | Human Factors; Detection | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Observation/reporting gaps | Low | High | Post-implementation Evaluation | Post-implementation
High cost of modifications after deployment | Testing, Quality & Evaluation Gaps | Financial | Financial; Maintenance | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Post-deployment cost | Low | High | Operations/Maintenance | Operations
Lack of simulation/testing leads to unforeseen errors | Testing, Quality & Evaluation Gaps | Governance | Quality; Risk Management | Canada | Tertiary / Teaching Hospitals | HIS Implementation | Insufficient pre-launch testing | Low | High | Planning/Testing | Planning/Design
Using quality measures as imperfect proxies for risk measures may miss critical safety signals | Risk Framework & Analytical Weaknesses | Governance | Measurement/Governance | USA | Tertiary / Teaching Hospitals | Risk Management Dashboard Development | Proxy limitations in measurement | High | High | Planning/Design | Planning/Design
Failure to include risk measures not amenable to classification undermines dashboard completeness | Risk Framework & Analytical Weaknesses | Governance | Measurement; Governance | USA | Tertiary / Teaching Hospitals | Risk Management Dashboard Development | Omission of qualitative indicators | High | High | Planning/Design | Planning/Design
Identifying the “most powerful and informative” measures is essential to dashboard effectiveness | Risk Framework & Analytical Weaknesses | Governance | Governance; Data Strategy | USA | Tertiary / Teaching Hospitals | Risk Management Dashboard Development | Selection bias risks in measure choice | High | High | Planning/Design | Planning/Design
Poor dashboard design (if visual best practices not used) can reduce interpretability and user trust | Testing, Quality & Evaluation Gaps | Workflow/Process | Usability; Visual Design | USA | Tertiary / Teaching Hospitals | Risk Management Dashboard Development | Visual miscommunication | High | High | Design/Development | Planning/Design
Inappropriate dashboard components may fail to support effective enterprise risk management evaluations | Testing, Quality & Evaluation Gaps | Governance | Process; Governance | USA | Tertiary / Teaching Hospitals | Risk Management Dashboard Development | Component mismatch with user needs | High | High | Design | Planning/Design
Healthcare complexity (non-uniform management, diverse staff, high innovation) increases latent failure risk | Organisational Performance & Benefits Realisation | Governance | Governance; Complexity | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | System complexity, latent failures | High | High | Initiation/Planning | Initiation
Risk management often lacks systemic perspective, undermining root-cause identification | Risk Framework & Analytical Weaknesses | Workflow/Process | Process; Methodology | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Narrow/focused risk analysis | High | High | Planning | Planning/Design
Failure to involve people in investigated processes limits decision-making support | Risk Framework & Analytical Weaknesses | Patient Engagement | People; Engagement | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Actor exclusion from analysis | High | High | Design/Analysis | Planning/Design
Ignoring human contributions in technical and organisational settings weakens reliability analysis | Risk Framework & Analytical Weaknesses | Technical | Human Factors; Technical | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Human-technology oversight gap | High | High | Design/Analysis | Planning/Design
Applying incomplete methods (not integrating HRA, PDCA, FTA etc.) yields inefficacy | Risk Framework & Analytical Weaknesses | Workflow/Process | Methodology; Quality | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Tool fragmentation risk | High | High | Design | Planning/Design
Limited validation (applied only to one pharmacy dept) raises generalizability risk | Testing, Quality & Evaluation Gaps | Governance | Strategy; Validity | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Single-site bias | High | High | Optimisation/Review | Post-implementation
Not covering non-clinical risks (focus only clinical) leaves gaps in risk coverage | Testing, Quality & Evaluation Gaps | Governance | Scope; Governance | Italy | Tertiary / Teaching Hospitals | Clinical Risk Management System | Non-clinical risk omission | High | High | Planning | Planning/Design
Poorly designed work systems create latent safety threats | Testing, Quality & Evaluation Gaps | Governance | Governance; Human Factors | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | System design flaws | Low | High | Initiation/Planning | Initiation
Ineffective communication between providers increases error risk | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; People | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Handoff errors, miscommunication | Low | High | Operations | Operations
Insufficient training leads to improper technology use | Human Resources, Training & User Support | Human Factors | Training; Human Factors | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Lack of competency building | Low | High | Deployment/Stabilisation | Deployment
Inadequate staffing or workload management causes fatigue-related errors | Human Resources, Training & User Support | Human Factors | Resource; Human Factors | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Overwork, fatigue | Low | High | Operations | Operations
Technology that does not fit workflow disrupts care delivery | Workflow & Process Misalignment | Technical | Technical; Workflow | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Workflow-tech misfit | Low | High | Design/Implementation | Implementation
Poor physical environment (lighting, noise, ergonomics) affects performance | Technical System & Infrastructure Failures | Human Factors | Infrastructure; Human Factors | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Environmental hazards | Low | High | Design/Implementation | Implementation
Misaligned organisational culture or policies undermine safety initiatives | Stakeholder, Leadership & Cultural Issues | Governance | Culture; Governance | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Cultural resistance | Low | High | Initiation/Planning | Initiation
Ignoring external environment factors (regulation, policy) leads to compliance risks | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory/Legal; Governance | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | Regulatory oversight gaps | Low | High | Planning | Planning/Design
Lack of feedback mechanisms prevents continuous safety improvement | Risk Framework & Analytical Weaknesses | Governance | Quality; Governance | USA | Tertiary / Teaching Hospitals | Patient Safety & Workflow Redesign | No learning loop | Low | High | Optimisation/Review | Post-implementation
Inadequate feasibility analysis before project start | Project Management & Governance Failures | Governance | Governance; Strategy | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Poor initial planning | Low | High | Initiation | Initiation
Unclear and shifting project scope | Project Management & Governance Failures | Governance | Process; Governance | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Scope creep | Low | High | Planning | Planning/Design
Lack of stakeholder engagement and user input | Stakeholder, Leadership & Cultural Issues | Human Factors | Stakeholder management; People | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Poor requirements gathering | Low | High | Planning/Design | Planning/Design
Vendor selection driven by non-technical/political factors | Vendor & External Dependence | Governance | Vendor/Procurement; Governance | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Political influence in procurement | Low | High | Procurement | Procurement
Poor project management and monitoring | Project Management & Governance Failures | Governance | Project management | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Lack of milestone tracking | Low | High | Execution | Execution
Inadequate technical infrastructure to support system | Technical System & Infrastructure Failures | Technical | Technical; Infrastructure | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Underestimated hardware/network needs | Low | High | Design/Implementation | Implementation
Lack of staff training and change management | Human Resources, Training & User Support | Human Factors | Training; Change management | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Resistance to change | Low | High | Deployment | Deployment
Over-reliance on external consultants | Vendor & External Dependence | Governance | Vendor/Procurement; People | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Limited internal capacity | Low | High | Implementation | Implementation
Poor alignment with organisational workflows | Workflow & Process Misalignment | Workflow/Process | Workflow; Process | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Workflow-system misfit | Low | High | Design/Implementation | Implementation
Cost overruns and budget mismanagement | Project Management & Governance Failures | Financial | Financial; Project management | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | Budget underestimation | Low | High | Execution | Execution
Failure to achieve intended clinical or operational benefits | Organisational Performance & Benefits Realisation | Governance | Clinical Safety; Strategy | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | ROI and outcomes gap | Low | High | Operations | Operations
Absence of post-implementation evaluation | Testing, Quality & Evaluation Gaps | Governance | Quality; Governance | USA | Tertiary / Teaching Hospitals | Healthcare IT Implementation | No lessons-learned process | Low | High | Optimisation/Review | Post-implementation
Heterogeneity in settings, users, indicators reduces generalizability | Risk Framework & Analytical Weaknesses | Governance | Strategy; Governance | Global/International | Tertiary / Teaching Hospitals | Clinical/Dashboard Implementation | Inconsistent contexts and measures | Low | High | Planning | Planning/Design
Variation in visual formats leads to inconsistent interpretation | Risk Framework & Analytical Weaknesses | Workflow/Process | Usability; Visual Design | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Varied charts and colors | Low | High | Design | Planning/Design
Poor evaluation study quality introduces bias | Risk Framework & Analytical Weaknesses | Workflow/Process | Quality; Methodology | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Low methodological rigor | Low | High | Evaluation | Post-implementation
Lack of evidence-based design guidelines hampers consistency | Risk Framework & Analytical Weaknesses | Governance | Governance; Strategy | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Absence of design standards | Low | High | Planning/Design | Planning/Design
Dashboards requiring active seeking reduces usage | Risk Framework & Analytical Weaknesses | Patient Engagement | Usability; Access | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Passive vs. active access | Low | High | Implementation | Implementation
Unknown impacts of dashboard type on clinician behavior | Risk Framework & Analytical Weaknesses | Workflow/Process | Clinical Safety; Impact | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Unintended behavior influence | Low | High | Operations | Operations
Research limited by rapid-review methods and search scope | Risk Framework & Analytical Weaknesses | Governance | Research Quality; Strategy | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Grey literature omitted | Low | High | Evaluation | Post-implementation
Difficulty in identifying eligible studies indicates search strategy challenges | Risk Framework & Analytical Weaknesses | Workflow/Process | Research Quality; Process | Global/International | Tertiary / Teaching Hospitals | Clinical Dashboard | Poor search specificity | Low | High | Planning | Planning/Design
Inadequate requirements gathering and analysis | Workflow & Process Misalignment | Workflow/Process | Process; Requirements | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Unclear or incomplete user needs | High | High | Planning | Planning/Design
Poor vendor selection and contract management | Vendor & External Dependence | Governance | Vendor/Procurement; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Weak selection criteria; SLA gaps | High | High | Procurement | Procurement
Lack of user involvement in design decisions | Stakeholder, Leadership & Cultural Issues | Human Factors | Stakeholder management; People | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | End-user exclusion | High | High | Design | Planning/Design
Misalignment between system design and clinical workflows | Workflow & Process Misalignment | Technical | Workflow; Technical | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Workflow–system mismatch | High | High | Design/Implementation | Implementation
Poor project management and oversight | Project Management & Governance Failures | Governance | Project management; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Weak monitoring; poor coordination | High | High | Execution | Execution
Inadequate training duration and scheduling | Human Resources, Training & User Support | Human Factors | Training; Change management | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Training too short or badly timed | High | High | Deployment/Stabilisation | Deployment
Technical defects in delivered system | Technical System & Infrastructure Failures | Technical | Technical; Quality | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Software bugs, errors | High | High | Testing/Deployment | Deployment
Lack of post-deployment support from vendor | Vendor & External Dependence | Governance | Vendor/Support | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | SLA non-compliance | High | High | Operations | Operations
Unclear project objectives and success criteria | Project Management & Governance Failures | Governance | Governance; Strategy | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | No shared definition of success | High | High | Initiation | Initiation
Scope creep during implementation | Project Management & Governance Failures | Governance | Process; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Requirements changing mid-project | High | High | Execution | Execution
Over-reliance on external consultants for core tasks | Vendor & External Dependence | Governance | Vendor/Procurement; HR | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Internal capacity gap | High | High | Implementation | Implementation
Failure to consider local context in system design | Workflow & Process Misalignment | Governance | Governance; Contextual | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Ignored organisational norms | High | High | Planning/Design | Planning/Design
Weak change management approach | Stakeholder, Leadership & Cultural Issues | Governance | Change management; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Resistance to change | High | High | Deployment | Deployment
Lack of comprehensive testing before go-live | Testing, Quality & Evaluation Gaps | Governance | Quality; Risk management | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Incomplete system validation | High | High | Testing | Deployment
Insufficient communication between stakeholders | Stakeholder, Leadership & Cultural Issues | Governance | Communication; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Coordination gaps | High | High | Execution | Execution
No clear escalation path for resolving issues | Project Management & Governance Failures | Governance | Governance; Process | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Delayed problem resolution | High | High | Execution | Execution
Unrealistic project timeline | Project Management & Governance Failures | Governance | Project management; Strategy | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Timeframe underestimation | High | High | Planning | Planning/Design
Failure to learn from previous similar projects | Project Management & Governance Failures | Governance | Knowledge management; Governance | Saudi Arabia | Tertiary / Teaching Hospitals | Healthcare software design & implementation | Ignored historical lessons | High | High | Initiation/Planning | Initiation
Standards & interoperability gaps hinder safe data exchange and HIE | Technical System & Infrastructure Failures | Technical | Standards; Interoperability; Technical | Global/International | Tertiary / Teaching Hospitals | EHR adoption & HIE | HL7/terminologies, data mapping | High | High | Design/Implementation | Implementation
Privacy & information‑security compliance burdens; breach risk | Regulatory, Legal & Policy Risks | Security/Privacy | Security/Privacy; Regulatory/Legal | Global/International | Tertiary / Teaching Hospitals | EHR adoption | HIPAA/compliance, infosec | High | High | Design/Operations | Operations
Ethical risks around secondary use/consent/data sharing | Regulatory, Legal & Policy Risks | Ethical/Legal | Ethics; Governance | Global/International | Tertiary / Teaching Hospitals | EHR adoption/analytics | Consent, secondary use | High | High | Planning/Operations | Operations
Usability problems create technology‑induced errors | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors; Clinical Safety | Global/International | Tertiary / Teaching Hospitals | EHR optimisation | Poor UI; safety hazards | High | High | Design/Operations | Operations
Alert fatigue from CDS leading to overrides/missed signals | Workflow & Process Misalignment | Workflow/Process | Clinical Safety; Decision Support; Usability | Global/International | Tertiary / Teaching Hospitals | CDS within EHR | Override behavior | High | High | Operations | Operations
Copy‑paste/template misuse degrades documentation integrity | Workflow & Process Misalignment | Data Quality | Data Quality; Clinical Safety | Global/International | Tertiary / Teaching Hospitals | EHR documentation | Note bloat; inaccurate notes | High | High | Operations | Operations
Information overload/cognitive burden on clinicians | Human Resources, Training & User Support | Workflow/Process | Usability; Human Factors | Global/International | Tertiary / Teaching Hospitals | EHR UI/content | Too many screens/alerts | High | High | Operations | Operations
Downtime/reliability & weak business continuity planning | Technical System & Infrastructure Failures | Governance | Infrastructure; Risk Management | Global/International | Tertiary / Teaching Hospitals | EHR operations | Outages; failover | High | High | Operations | Operations
Patient identification/matching errors; duplicate records | Technical System & Infrastructure Failures | Data Quality | Data Quality; Safety; Process | Global/International | Tertiary / Teaching Hospitals | MPI/HIE within EHR | Duplicate MRNs, mismatches | High | High | Design/Operations | Operations
Terminology/coding/mapping issues harm data quality & reuse | Technical System & Infrastructure Failures | Data Quality | Standards; Data Quality | Global/International | Tertiary / Teaching Hospitals | EHR data governance | SNOMED/LOINC mapping | High | High | Design/Operations | Operations
Insufficient clinician competencies/training for EHR use | Human Resources, Training & User Support | Human Factors | Training/Education; People | Global/International | Tertiary / Teaching Hospitals | Training & simulation | Informatics competencies | High | High | Deployment/Operations | Deployment
Productivity loss & documentation burden post‑go‑live | Human Resources, Training & User Support | Human Factors | Operations; Human Factors | Global/International | Tertiary / Teaching Hospitals | EHR rollout | Time on documentation | High | High | Deployment/Operations | Deployment
Workflow misalignment; workarounds & unsafe practices | Workflow & Process Misalignment | Human Factors | Process/Workflow; Change management | Global/International | Tertiary / Teaching Hospitals | EHR implementation | Workarounds | High | High | Design/Implementation | Implementation
Policy/program misalignment (e.g., targets/“meaningful use”) vs clinical reality | Regulatory, Legal & Policy Risks | Ethical/Legal | Governance; Strategy; Regulatory | Global/International | Tertiary / Teaching Hospitals | Compliance‑driven EHR | Metrics ≠ care needs | High | High | Planning/Operations | Operations
Vendor lock‑in limits portability/customisation/innovation | Vendor & External Dependence | Governance | Vendor/Procurement; Strategy | Global/International | Tertiary / Teaching Hospitals | EHR procurement | Proprietary constraints | High | High | Procurement/Operations | Procurement
Cross‑setting integration gaps (acute/ambulatory/social care) | Technical System & Infrastructure Failures | Technical | Interoperability; Integration | Global/International | Tertiary / Teaching Hospitals | HIE/continuity of care | Fragmentation | High | High | Implementation/Operations | Implementation
Integrating genomics/wearables/external knowledge resources remains difficult | Technical System & Infrastructure Failures | Technical | Data Integration; Technical | Global/International | Tertiary / Teaching Hospitals | Advanced EHR | Genomics; infobuttons | High | High | Design/Operations | Operations
Lack of explicit oversight infrastructure for EHR‑related safety hazards | Project Management & Governance Failures | Governance | Governance; Patient Safety | Global/International | Tertiary / Teaching Hospitals | EHR safety management | Safety oversight gaps | High | High | Operations | Operations
Quality improvement isn’t automatic with EHRs; requires redesign | Workflow & Process Misalignment | Governance | Quality; Governance; Process | Global/International | Tertiary / Teaching Hospitals | EHR optimisation | QI not automatic | High | High | Optimisation/Review | Post-implementation
Patient portal engagement barriers & digital divide concerns | Human Resources, Training & User Support | Patient Engagement | Access; Social Factors | Global/International | Tertiary / Teaching Hospitals | Patient engagement | Adoption disparities | High | High | Operations | Operations
Limited literature available on dashboards in clinical settings | Risk Framework & Analytical Weaknesses | Workflow/Process | Research Quality; Evidence Base | Global/International | Tertiary / Teaching Hospitals | Visualisation dashboard evaluation | Sparse evidence | Low | High | Planning/Design | Planning/Design
Risk of confirmation bias in small study bodies; limited generalizability | Risk Framework & Analytical Weaknesses | Workflow/Process | Methodology; Generalizability | Global/International | Tertiary / Teaching Hospitals | Dashboard studies | 17 articles only | Low | High | Evaluation | Post-implementation
Cognitive overload persists despite dashboards in complex ICU settings | Human Resources, Training & User Support | Human Factors | Human Factors; Cognitive Load | USA | Tertiary / Teaching Hospitals | ICU dashboards | High cognitive demand persisted | Low | High | Operations | Operations
Dashboard designs may not have accounted for ICU clinicians’ mental models or workflow | Workflow & Process Misalignment | Workflow/Process | Usability; Workflow Fit | USA | Tertiary / Teaching Hospitals | ICU visualisation | Poor alignment with clinical workflow | Low | High | Design/Implementation | Implementation
Risk of workflow disruption or unintended consequences due to interface usability issues | Workflow & Process Misalignment | Workflow/Process | Usability; Task Disruption | USA | Tertiary / Teaching Hospitals | ICU dashboards | Interface disrupting care | Low | High | Implementation/Operations | Implementation
Potential for over-reliance on dashboard prompting, causing complacency | Risk Framework & Analytical Weaknesses | Human Factors | Human Factors; Clinical Safety | USA | Tertiary / Teaching Hospitals | ICU dashboards | Over-reliance risk | Low | High | Operations | Operations
Integration failures with LIS or lab systems may lead to delayed or lost orders | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Europe | Tertiary / Teaching Hospitals | Lab test request module within EHR | LIS integration | Low | Medium | Design/Implementation | Implementation
User interface/usability issues could cause incorrect test requests | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors | Europe | Tertiary / Teaching Hospitals | Lab test request module | UI complexity | Low | Medium | Design | Planning/Design
Minimal evaluation sample or bias limits generalizability of module usability | Testing, Quality & Evaluation Gaps | Workflow/Process | Research Quality; Evidence Base | Europe | Tertiary / Teaching Hospitals | Lab test request module evaluation | Small sample ‑ biased | Low | Medium | Evaluation | Post-implementation
Risk of requesting unnecessary or duplicate tests if logic lacks validation | Testing, Quality & Evaluation Gaps | Workflow/Process | Clinical Safety; Process | Europe | Tertiary / Teaching Hospitals | Lab test request module | Duplicate/unnecessary tests | Low | Medium | Design/Implementation | Implementation
Administrative burden if module design doesn't streamline daily lab request workflows | Workflow & Process Misalignment | Workflow/Process | Workflow; Efficiency | Europe | Tertiary / Teaching Hospitals | Lab test request module | Added workflow strain | Low | Medium | Implementation | Implementation
Poor stakeholder involvement (e.g. lab personnel feedback) may affect module fit | Stakeholder, Leadership & Cultural Issues | Human Factors | Stakeholder management; People | Europe | Tertiary / Teaching Hospitals | Lab test request module | Lab staff exclusion | Low | Medium | Design | Planning/Design
Failure to scale BI solutions from pilot to enterprise-wide deployments | Project Management & Governance Failures | Technical | Scalability; Implementation | Italy | Tertiary / Teaching Hospitals | BI maturity roadmap towards precision medicine | Pilots vs scale | Medium | Medium | Implementation | Implementation
Lack of clear maturity model leading to unprioritized development | Risk Framework & Analytical Weaknesses | Governance | Strategy; Governance | Italy | Tertiary / Teaching Hospitals | BI maturity model development | No maturity framework | Medium | Medium | Planning | Planning/Design
Misalignment between BI capabilities and organisational readiness | Workflow & Process Misalignment | Human Factors | Organisational Readiness; Change Management | Italy | Tertiary / Teaching Hospitals | BI maturity roadmap | Readiness gap | Medium | Medium | Planning | Planning/Design
Risk of roadmaps not accounting for interdependencies between BI dimensions | Project Management & Governance Failures | Technical | Process; Integration | Italy | Tertiary / Teaching Hospitals | BI maturity dimensions | Dimension interdependency | Medium | Medium | Design/Implementation | Implementation
Insufficient benchmarking and continuous improvement tracking | Risk Framework & Analytical Weaknesses | Workflow/Process | Quality; Process Improvement | Italy | Tertiary / Teaching Hospitals | BI maturity assessment | Lack of benchmarking | Medium | Medium | Operations | Operations
Maturity assessment questionnaire bias due to limited stakeholder representation | Risk Framework & Analytical Weaknesses | Governance | Research Quality; Stakeholder Engagement | Italy | Tertiary / Teaching Hospitals | BI maturity measurement | Biased self-assessment | Medium | Medium | Evaluation | Post-implementation
Static reporting systems produce inconsistent, incomparable, time‑consuming reports | Risk Framework & Analytical Weaknesses | Workflow/Process | Reporting Quality; Efficiency | Global/International | Tertiary / Teaching Hospitals | Literature review of dashboards | Static legacy systems | Medium | Medium | Context / Baseline | Cross-phase
Focusing on few KPIs risks ignoring key areas; fragmented measures impair fairness | Risk Framework & Analytical Weaknesses | Governance | KPI selection; Strategy | Global/International | Tertiary / Teaching Hospitals | Dashboard designing | Narrow, inconsistent KPIs | Medium | Medium | Planning / Design | Planning/Design
Poor data quality or mismatched sources compromise dashboard accuracy and reliability | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Global/International | Tertiary / Teaching Hospitals | Dashboard designing | Source mismatch / poor quality | Medium | Medium | Design / Implementation | Implementation
Integration issues prevent dashboards updating dynamically, reducing decision utility | Technical System & Infrastructure Failures | Technical | Integration; Technical | Global/International | Tertiary / Teaching Hospitals | Dashboard designing | Poor system integration | Medium | Medium | Implementation | Implementation
Poor information presentation (clutter, poor design) reduces usability | Testing, Quality & Evaluation Gaps | Workflow/Process | Usability; Visual Design | Global/International | Tertiary / Teaching Hospitals | Dashboard designing | Ineffective UI/visualisation | Medium | Medium | Design / Implementation | Implementation
Lack of top management support limits adoption of advanced dashboards | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Org Support | Global/International | Tertiary / Teaching Hospitals | Dashboard adoption | No executive sponsorship | Medium | Medium | Planning / Execution | Execution
High cost of infrastructure (warehousing, training, customisation) may hinder sustainability | Financial & Resource Constraints | Financial | Cost; Infrastructure | Global/International | Tertiary / Teaching Hospitals | Dashboard adoption | High costs | Medium | Medium | Planning / Operations | Operations
Focus only on design phase leaves lifecycle phases like maintenance unaddressed | Testing, Quality & Evaluation Gaps | Governance | Lifecycle Coverage; Scope | Global/International | Tertiary / Teaching Hospitals | Research methodology | Lifecycle phase omission | Medium | Medium | Study Scope (meta) | Cross-phase
Lack of strong evidence on spread and sustainability of innovations | Risk Framework & Analytical Weaknesses | Workflow/Process | Research Quality; Evidence Base | Global/International | Tertiary / Teaching Hospitals | Innovation adoption in health services | Weak empirical base | Low | High | Planning | Planning/Design
Organisational readiness not assessed before adoption | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Organisational Readiness | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Readiness gap | Low | High | Planning | Planning/Design
Failure to align innovation with organisational culture and values | Stakeholder, Leadership & Cultural Issues | Governance | Culture; Governance | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Cultural misfit | Low | High | Planning/Design | Planning/Design
Inadequate leadership and top management support | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Leadership | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Weak leadership backing | Low | High | Planning/Implementation | Planning/Design
Poor communication between stakeholders hinders diffusion | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; Stakeholder management | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Communication gaps | Low | High | Implementation | Implementation
Lack of adaptation of the innovation to local context | Workflow & Process Misalignment | Governance | Adaptability; Governance | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Ignored contextual needs | Low | High | Design/Implementation | Implementation
No evaluation/feedback mechanisms to monitor spread | Testing, Quality & Evaluation Gaps | Governance | Monitoring/Evaluation; Governance | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Missing continuous evaluation | Low | High | Optimisation | Post-implementation
Complexity of innovation deters adoption | Workflow & Process Misalignment | Workflow/Process | Complexity; Usability | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Steep learning curve | Low | High | Planning/Implementation | Planning/Design
Lack of resources (time, staff, funds) for scaling up | Financial & Resource Constraints | Financial | Resources; Financial | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Resource scarcity | Low | High | Implementation/Scaling | Implementation
Policy and regulatory misalignment with innovation | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Policy conflict | Low | High | Planning | Planning/Design
Over-reliance on opinion leaders without broader engagement | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management; Governance | Global/International | Tertiary / Teaching Hospitals | Innovation adoption | Leadership bottleneck | Low | High | Implementation | Implementation
EHR data entry detracts from direct patient interaction | Workflow & Process Misalignment | Workflow/Process | Workflow; Human Factors | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Clinician–patient interaction loss | Low | High | Operations | Operations
Increased documentation workload burdens clinicians | Human Resources, Training & User Support | Workflow/Process | Workload; Efficiency | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Time-consuming documentation | Low | High | Operations | Operations
Protocol-driven prompts may undermine clinical judgment/autonomy | Workflow & Process Misalignment | Workflow/Process | Clinical Autonomy; Usability | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Protocol dominance | Low | High | Design/Operations | Operations
Misalignment between EHR design and clinical workflow | Workflow & Process Misalignment | Workflow/Process | Usability; Workflow Fit | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Design–practice gap | Low | High | Design/Implementation | Implementation
Information fragmentation across modules impedes holistic care | Workflow & Process Misalignment | Data Quality | Data Quality; Integration | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Fragmented patient info | Low | High | Implementation | Implementation
Inflexible system customisation limits adaptation to local needs | Workflow & Process Misalignment | Governance | Adaptability; Governance | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Limited local tailoring | Low | High | Design | Planning/Design
Over-reliance on coded data entry misses nuanced clinical context | Workflow & Process Misalignment | Data Quality | Data Quality; Clinical Safety | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Loss of narrative richness | Low | High | Operations | Operations
Inadequate training/support leads to poor adoption and errors | Human Resources, Training & User Support | Human Factors | Training; Change management | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Insufficient skills support | Low | High | Deployment/Operations | Deployment
Resistance from clinicians who perceive EHR as managerial surveillance | Stakeholder, Leadership & Cultural Issues | Governance | Culture; Trust; Governance | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Surveillance fears | Low | High | Planning/Deployment | Deployment
Lack of interoperability with external systems disrupts continuity of care | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | UK | Tertiary / Teaching Hospitals | EHR implementation & use | HIE gaps | Low | High | Implementation | Implementation
Poor search/navigation design slows information retrieval | Workflow & Process Misalignment | Workflow/Process | Usability; Efficiency | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Navigation inefficiency | Low | High | Operations | Operations
Tension between clinical and administrative priorities in EHR use | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Workflow | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Competing priorities | Low | High | Operations | Operations
Unclear accountability for data quality and completeness | Project Management & Governance Failures | Governance | Governance; Data Quality | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Accountability gaps | Low | High | Operations | Operations
Alerts and reminders create cognitive overload | Workflow & Process Misalignment | Workflow/Process | Clinical Safety; Usability | UK | Tertiary / Teaching Hospitals | EHR implementation & use | Alert fatigue | Low | High | Operations | Operations
Significant productivity loss during and after transition | Human Resources, Training & User Support | Human Factors | Operations; Human Factors | USA | Tertiary / Teaching Hospitals | EHR replacement | Drop in clinical throughput | High | High | Deployment/Operations | Deployment
Increased clinician frustration and burnout from learning curve | Human Resources, Training & User Support | Human Factors | Human Factors; Change management | USA | Tertiary / Teaching Hospitals | EHR replacement | Learning curve fatigue | High | High | Deployment | Deployment
Data migration errors and incomplete data transfer | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | USA | Tertiary / Teaching Hospitals | EHR replacement | Migration integrity risk | High | High | Implementation | Implementation
Loss of historical data context due to format or mapping issues | Technical System & Infrastructure Failures | Data Quality | Data Quality; Interoperability | USA | Tertiary / Teaching Hospitals | EHR replacement | Context loss in migration | High | High | Implementation | Implementation
Workflow disruption and inefficiency in redesigned processes | Workflow & Process Misalignment | Workflow/Process | Workflow; Usability | USA | Tertiary / Teaching Hospitals | EHR replacement | Misaligned workflows | High | High | Design/Implementation | Implementation
Inadequate stakeholder engagement in configuration decisions | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management; Governance | USA | Tertiary / Teaching Hospitals | EHR replacement | Lack of user input | High | High | Planning/Design | Planning/Design
Loss of customisation or specialty-specific features | Workflow & Process Misalignment | Workflow/Process | Adaptability; Clinical Safety | USA | Tertiary / Teaching Hospitals | EHR replacement | Feature regression | High | High | Implementation | Implementation
Insufficient training prior to go-live | Human Resources, Training & User Support | Human Factors | Training; Change management | USA | Tertiary / Teaching Hospitals | EHR replacement | Training gap | High | High | Deployment | Deployment
Inadequate post-go-live support | Vendor & External Dependence | Governance | Vendor management; Support | USA | Tertiary / Teaching Hospitals | EHR replacement | Lack of at-elbow help | High | High | Operations | Operations
Increased patient safety risks during transition due to unfamiliarity | Workflow & Process Misalignment | Human Factors | Clinical Safety; Human Factors | USA | Tertiary / Teaching Hospitals | EHR replacement | Risk of errors | High | High | Deployment/Operations | Deployment
Over-reliance on vendor recommendations without local adaptation | Vendor & External Dependence | Governance | Vendor management; Governance | USA | Tertiary / Teaching Hospitals | EHR replacement | Vendor-driven decisions | High | High | Planning/Design | Planning/Design
Cost overruns and budget strain | Financial & Resource Constraints | Financial | Financial; Governance | USA | Tertiary / Teaching Hospitals | EHR replacement | Budget overrun | High | High | Implementation | Implementation
Regulatory compliance gaps during transition period | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | USA | Tertiary / Teaching Hospitals | EHR replacement | Temporary non-compliance | High | High | Implementation/Operations | Implementation
Unauthorized access to EDI systems due to weak authentication | Security & Cyber Risks | Security/Privacy | Security; Technical | USA | Mixed Healthcare Organisations | EDI security | Weak authentication controls | High | High | Operations | Operations
Insider threats from privileged users | Security & Cyber Risks | Security/Privacy | Security; Governance | USA | Mixed Healthcare Organisations | EDI security | Insider misuse risk | High | High | Operations | Operations
Lack of encryption during EDI data transmission | Security & Cyber Risks | Security/Privacy | Security; Technical | USA | Mixed Healthcare Organisations | EDI security | Unencrypted transfers | High | High | Design/Implementation | Implementation
Outdated or unpatched EDI software vulnerable to exploits | Security & Cyber Risks | Security/Privacy | Security; Technical | USA | Mixed Healthcare Organisations | EDI security | Patch management gaps | High | High | Operations | Operations
Insufficient employee training on EDI security protocols | Human Resources, Training & User Support | Human Factors | Training; Human Factors | USA | Mixed Healthcare Organisations | EDI security | Training gaps | High | High | Deployment/Operations | Deployment
Non-compliance with HIPAA and other regulations | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | USA | Mixed Healthcare Organisations | EDI security | Compliance violations | High | High | Operations | Operations
Poor vendor management and third-party risk | Vendor & External Dependence | Governance | Vendor management; Governance | USA | Mixed Healthcare Organisations | EDI security | Vendor trust gap | High | High | Planning/Operations | Operations
Lack of continuous monitoring for suspicious activity | Security & Cyber Risks | Security/Privacy | Monitoring; Security | USA | Mixed Healthcare Organisations | EDI security | No real-time alerts | High | High | Operations | Operations
Weak incident response planning for EDI breaches | Security & Cyber Risks | Security/Privacy | Governance; Security | USA | Mixed Healthcare Organisations | EDI security | No IRP or drill | High | High | Planning/Operations | Operations
Inadequate segregation of duties in EDI workflows | Security & Cyber Risks | Governance | Governance; Process | USA | Mixed Healthcare Organisations | EDI security | SoD violations | High | High | Planning/Operations | Operations
Data integrity risks from incomplete or erroneous EDI transactions | Security & Cyber Risks | Data Quality | Data Quality; Security | USA | Mixed Healthcare Organisations | EDI security | Transaction errors | High | High | Operations | Operations
Over-reliance on legacy EDI infrastructure with limited scalability | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | USA | Mixed Healthcare Organisations | EDI security | Legacy dependency | High | High | Planning/Implementation | Planning/Design
Physical security gaps for EDI servers or terminals | Security & Cyber Risks | Security/Privacy | Physical Security; Infrastructure | USA | Mixed Healthcare Organisations | EDI security | Physical access risk | High | High | Operations | Operations
Cybersecurity threats from increased digitalisation | Security & Cyber Risks | Security/Privacy | Security; Technical | Global/International | All Hospital Types | Digital transformation in healthcare | Data breaches; ransomware | High | High | Operations | Operations
Compliance burden with evolving healthcare regulations | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | Global/International | All Hospital Types | Digital transformation in healthcare | HIPAA/GDPR compliance | High | High | Operations | Operations
High cost of technology implementation and maintenance | Financial & Resource Constraints | Financial | Financial; Infrastructure | Global/International | All Hospital Types | Digital transformation in healthcare | Cost overruns; sustainability | High | High | Planning/Operations | Operations
Interoperability issues between disparate healthcare systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Global/International | All Hospital Types | Digital transformation in healthcare | Integration failures | High | High | Design/Implementation | Implementation
Resistance to change from healthcare staff | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Human Factors | Global/International | All Hospital Types | Digital transformation in healthcare | Cultural resistance | High | High | Planning/Deployment | Deployment
Data privacy concerns with patient-facing apps and IoT devices | Regulatory, Legal & Policy Risks | Security/Privacy | Security; Privacy | Global/International | All Hospital Types | Digital transformation in healthcare | Wearables; patient portals | High | High | Operations | Operations
Shortage of skilled professionals for managing advanced health IT | Human Resources, Training & User Support | Human Factors | Workforce; Training | Global/International | All Hospital Types | Digital transformation in healthcare | Skills gap | High | High | Planning/Operations | Operations
Reliability issues with telehealth and remote monitoring tools | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Global/International | All Hospital Types | Digital transformation in healthcare | Network downtime | High | High | Operations | Operations
Ethical concerns over AI-driven decision making in patient care | Regulatory, Legal & Policy Risks | Ethical/Legal | Ethics; Clinical Safety | Global/International | All Hospital Types | Digital transformation in healthcare | AI bias; transparency | High | High | Design/Operations | Operations
Communication breakdowns between patients and staff | Stakeholder, Leadership & Cultural Issues | Human Factors | Communication; Human Factors | UK | Tertiary / Teaching Hospitals | Service quality improvement | Miscommunication | High | High | Operations | Operations
Long wait times reducing perceived service quality | Organisational Performance & Benefits Realisation | Workflow/Process | Efficiency; Workflow | UK | Tertiary / Teaching Hospitals | Service quality improvement | Waiting time | High | High | Operations | Operations
Inadequate information provision about care processes | Organisational Performance & Benefits Realisation | Governance | Communication; Governance | UK | Tertiary / Teaching Hospitals | Service quality improvement | Lack of transparency | High | High | Operations | Operations
Lack of personalisation in patient interactions | Organisational Performance & Benefits Realisation | Workflow/Process | Human Factors; Service Design | UK | Tertiary / Teaching Hospitals | Service quality improvement | One-size-fits-all approach | High | High | Design/Operations | Operations
Poor coordination across departments impacting care continuity | Stakeholder, Leadership & Cultural Issues | Technical | Workflow; Integration | UK | Tertiary / Teaching Hospitals | Service quality improvement | Cross-department gaps | High | High | Implementation/Operations | Implementation
Unmet emotional support needs for patients | Organisational Performance & Benefits Realisation | Workflow/Process | Human Factors; Service Design | UK | Tertiary / Teaching Hospitals | Service quality improvement | Lack of empathy/support | High | High | Operations | Operations
Environment and facilities not meeting patient expectations | Organisational Performance & Benefits Realisation | Human Factors | Infrastructure; Human Factors | UK | Tertiary / Teaching Hospitals | Service quality improvement | Poor physical environment | High | High | Operations | Operations
Staff shortages affecting service delivery | Human Resources, Training & User Support | Governance | Workforce; Governance | UK | Tertiary / Teaching Hospitals | Service quality improvement | Understaffing | High | High | Operations | Operations
Lack of patient involvement in decision-making | Stakeholder, Leadership & Cultural Issues | Patient Engagement | Governance; Patient Engagement | UK | Tertiary / Teaching Hospitals | Service quality improvement | Exclusion from decisions | High | High | Planning/Operations | Operations
Inconsistent service quality across different hospital areas | Organisational Performance & Benefits Realisation | Governance | Quality; Governance | UK | Tertiary / Teaching Hospitals | Service quality improvement | Variability in care | High | High | Operations | Operations
Incomplete or inaccurate user requirements | Workflow & Process Misalignment | Workflow/Process | Requirements; Process | Iran | Tertiary / Teaching Hospitals | HIS implementation | Requirements gap | Medium | Medium | Planning | Planning/Design
Lack of user training and technical skills | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Iran | Tertiary / Teaching Hospitals | HIS implementation | Training deficiency | Medium | Medium | Deployment | Deployment
Resistance to change among staff | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Human Factors | Iran | Tertiary / Teaching Hospitals | HIS implementation | Cultural resistance | Medium | Medium | Planning/Deployment | Deployment
Poor integration with existing systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Iran | Tertiary / Teaching Hospitals | HIS implementation | System incompatibility | Medium | Medium | Design/Implementation | Implementation
Low data quality and incomplete patient records | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Iran | Tertiary / Teaching Hospitals | HIS implementation | Inaccurate/incomplete records | Medium | Medium | Operations | Operations
Hardware or network failures | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Iran | Tertiary / Teaching Hospitals | HIS implementation | Downtime risk | Medium | Medium | Operations | Operations
Vendor support deficiencies | Vendor & External Dependence | Governance | Vendor management; Governance | Iran | Tertiary / Teaching Hospitals | HIS implementation | Poor post-go-live support | Medium | Medium | Operations | Operations
Security vulnerabilities in HIS software | Security & Cyber Risks | Security/Privacy | Security; Technical | Iran | Tertiary / Teaching Hospitals | HIS implementation | Cybersecurity gaps | Medium | Medium | Operations | Operations
Lack of continuous monitoring and performance evaluation | Project Management & Governance Failures | Governance | Governance; Monitoring | Iran | Tertiary / Teaching Hospitals | HIS implementation | No ongoing evaluation | Medium | Medium | Operations | Operations
Delays in project timeline | Project Management & Governance Failures | Governance | Project management; Governance | Iran | Tertiary / Teaching Hospitals | HIS implementation | Schedule slippage | Medium | Medium | Implementation | Implementation
Insufficient budget for complete implementation | Financial & Resource Constraints | Financial | Financial; Governance | Iran | Tertiary / Teaching Hospitals | HIS implementation | Budget shortfall | Medium | Medium | Planning | Planning/Design
Misalignment between analytics project goals and hospital strategic priorities | Workflow & Process Misalignment | Governance | Governance; Strategy | USA | Tertiary / Teaching Hospitals | Analytics implementation | Strategic misfit | High | High | Planning | Planning/Design
Lack of stakeholder buy-in and engagement | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management; Governance | USA | Tertiary / Teaching Hospitals | Analytics implementation | Low engagement | High | High | Planning/Implementation | Planning/Design
Poor data quality affecting model accuracy | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | USA | Tertiary / Teaching Hospitals | Analytics implementation | Inaccurate/incomplete data | High | High | Design/Implementation | Implementation
Insufficient data integration across hospital systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | USA | Tertiary / Teaching Hospitals | Analytics implementation | Integration gaps | High | High | Design/Implementation | Implementation
Limited technical skills among staff to support analytics tools | Human Resources, Training & User Support | Human Factors | Workforce; Training | USA | Tertiary / Teaching Hospitals | Analytics implementation | Skills gap | High | High | Planning/Deployment | Deployment
Overly complex analytics solutions leading to low adoption | Workflow & Process Misalignment | Workflow/Process | Usability; Complexity | USA | Tertiary / Teaching Hospitals | Analytics implementation | Complexity barrier | High | High | Implementation/Operations | Implementation
Lack of timely feedback loops to refine analytics outputs | Risk Framework & Analytical Weaknesses | Governance | Monitoring; Governance | USA | Tertiary / Teaching Hospitals | Analytics implementation | No iteration | High | High | Operations | Operations
Failure to adequately pilot solutions before scaling | Testing, Quality & Evaluation Gaps | Governance | Project management; Risk management | USA | Tertiary / Teaching Hospitals | Analytics implementation | Skipped pilot phase | High | High | Implementation | Implementation
Resistance to workflow changes introduced by analytics tools | Workflow & Process Misalignment | Human Factors | Change management; Human Factors | USA | Tertiary / Teaching Hospitals | Analytics implementation | Change resistance | High | High | Deployment/Operations | Deployment
Insufficient funding for long-term analytics maintenance | Financial & Resource Constraints | Financial | Financial; Sustainability | USA | Tertiary / Teaching Hospitals | Analytics implementation | Funding gap | High | High | Operations | Operations
Limited interoperability between primary care and other providers | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Global/International | Primary Care Practices | HIT adoption | Data exchange gaps | Medium | Medium | Design/Implementation | Implementation
Inconsistent availability of patient summaries and care plans | Technical System & Infrastructure Failures | Data Quality | Data Quality; Process | Global/International | Primary Care Practices | HIT adoption | Missing summaries | Medium | Medium | Operations | Operations
Low use of electronic prescribing in some countries | Technical System & Infrastructure Failures | Technical | Adoption; Technical | Global/International | Primary Care Practices | ePrescribing | eRx underutilisation | Medium | Medium | Operations | Operations
Few primary care doctors can email patients directly | Workflow & Process Misalignment | Patient Engagement | Communication; Access | Global/International | Primary Care Practices | HIT adoption | Limited patient messaging | Medium | Medium | Operations | Operations
Limited use of IT for patient engagement tools | Organisational Performance & Benefits Realisation | Patient Engagement | Patient Engagement; Technical | Global/International | Primary Care Practices | HIT adoption | Engagement tool gaps | Medium | Medium | Operations | Operations
Variation in IT adoption rates across countries | Organisational Performance & Benefits Realisation | Governance | Governance; Strategy | Global/International | Primary Care Practices | HIT adoption | Adoption disparity | Medium | Medium | Planning | Planning/Design
Lack of financial incentives/support for IT adoption in some countries | Financial & Resource Constraints | Financial | Financial; Governance | Global/International | Primary Care Practices | HIT adoption | Incentive gaps | Medium | Medium | Planning | Planning/Design
Technical barriers such as cost and lack of support | Financial & Resource Constraints | Financial | Technical; Financial | Global/International | Primary Care Practices | HIT adoption | Infrastructure constraints | Medium | Medium | Planning/Implementation | Planning/Design
Limited ability to coordinate with specialists or hospitals electronically | Workflow & Process Misalignment | Technical | Interoperability; Process | Global/International | Primary Care Practices | HIT adoption | Care coordination gaps | Medium | Medium | Implementation/Operations | Implementation
Data quality issues due to incomplete, inconsistent, or erroneous source data | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Inaccurate datasets | Low | Medium | Design/Implementation | Implementation
Lack of interoperability with other hospital systems and EHRs | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Integration gaps | Low | Medium | Design/Implementation | Implementation
Limited data governance frameworks leading to uncontrolled access | Regulatory, Legal & Policy Risks | Security/Privacy | Governance; Security | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Governance gaps | Low | Medium | Planning/Operations | Operations
Inadequate user training for effective use of dashboards | Human Resources, Training & User Support | Human Factors | Training; Human Factors | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Training shortfall | Low | Medium | Deployment/Operations | Deployment
Dependence on manual data preparation and cleaning | Workflow & Process Misalignment | Workflow/Process | Process; Efficiency | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Manual workload | Low | Medium | Implementation | Implementation
Potential data security risks when connecting to cloud services | Security & Cyber Risks | Security/Privacy | Security; Technical | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Cloud data risk | Low | Medium | Implementation/Operations | Implementation
Scalability limitations for handling large, complex datasets | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Performance bottlenecks | Low | Medium | Implementation/Operations | Implementation
Lack of real-time data processing capabilities | Technical System & Infrastructure Failures | Technical | Technical; Timeliness | India | Multi-Specialty Hospitals | Healthcare analytics using Power BI | Batch processing delays | Low | Medium | Operations | Operations
Hardware/software failures impacting clinical operations | Technical System & Infrastructure Failures | Technical | Technical; Infrastructure | Global/International | All Hospital Types | HIT in complex adaptive systems | System downtime | High | High | Operations | Operations
Poor user interface design leading to usability issues | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors | Global/International | All Hospital Types | HIT in complex adaptive systems | Design flaws | High | High | Design/Implementation | Implementation
Inadequate clinical content within systems (e.g., incomplete order sets, protocols) | Workflow & Process Misalignment | Data Quality | Clinical Safety; Data Quality | Global/International | All Hospital Types | HIT in complex adaptive systems | Missing/inaccurate content | High | High | Design/Implementation | Implementation
Workflow misalignment between HIT and clinical processes | Workflow & Process Misalignment | Human Factors | Workflow; Change management | Global/International | All Hospital Types | HIT in complex adaptive systems | Process mismatch | High | High | Design/Implementation | Implementation
Organisational culture resistant to HIT adoption | Stakeholder, Leadership & Cultural Issues | Governance | Culture; Governance | Global/International | All Hospital Types | HIT in complex adaptive systems | Resistance to change | High | High | Planning/Deployment | Deployment
Inadequate policies and procedures to support safe HIT use | Project Management & Governance Failures | Governance | Governance; Policy | Global/International | All Hospital Types | HIT in complex adaptive systems | Policy gaps | High | High | Planning/Operations | Operations
Insufficient system monitoring and maintenance | Project Management & Governance Failures | Technical | Monitoring; Technical | Global/International | All Hospital Types | HIT in complex adaptive systems | No proactive checks | High | High | Operations | Operations
Ineffective communication and coordination among stakeholders | Stakeholder, Leadership & Cultural Issues | Governance | Communication; Governance | Global/International | All Hospital Types | HIT in complex adaptive systems | Collaboration breakdown | High | High | Implementation/Operations | Implementation
Lack of training and ongoing education for HIT users | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Global/International | All Hospital Types | HIT in complex adaptive systems | Skills gap | High | High | Deployment/Operations | Deployment
External regulations and standards not adequately addressed | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | Global/International | All Hospital Types | HIT in complex adaptive systems | Compliance risk | High | High | Planning/Operations | Operations
Inadequate vendor support and collaboration | Vendor & External Dependence | Governance | Vendor management; Governance | Global/International | All Hospital Types | HIT in complex adaptive systems | Vendor relationship gaps | High | High | Operations | Operations
Over-reliance on technology without sufficient human oversight | Workflow & Process Misalignment | Human Factors | Clinical Safety; Human Factors | Global/International | All Hospital Types | HIT in complex adaptive systems | Automation bias | High | High | Operations | Operations
Misalignment between ERP design and healthcare workflows | Workflow & Process Misalignment | Workflow/Process | Workflow; Usability | Greece | Public General Hospitals | ERP integration | Process mismatch | Low | Medium | Design/Implementation | Implementation
Resistance from clinical and administrative staff to ERP adoption | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Human Factors | Greece | Public General Hospitals | ERP integration | Cultural resistance | Low | Medium | Planning/Deployment | Deployment
Poor data migration leading to inaccurate records in ERP | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Greece | Public General Hospitals | ERP integration | Migration errors | Low | Medium | Implementation | Implementation
Lack of interoperability between ERP and specialized clinical systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Greece | Public General Hospitals | ERP integration | Integration gaps | Low | Medium | Design/Implementation | Implementation
Limited ERP customisation for healthcare-specific needs | Workflow & Process Misalignment | Governance | Adaptability; Governance | Greece | Public General Hospitals | ERP integration | Limited tailoring | Low | Medium | Design | Planning/Design
Insufficient training for users on ERP modules | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Greece | Public General Hospitals | ERP integration | Skills gap | Low | Medium | Deployment | Deployment
Budget overruns during ERP implementation | Financial & Resource Constraints | Financial | Financial; Governance | Greece | Public General Hospitals | ERP integration | Cost overrun | Low | Medium | Implementation | Implementation
Project delays due to complexity of ERP integration | Project Management & Governance Failures | Governance | Project management; Governance | Greece | Public General Hospitals | ERP integration | Schedule slippage | Low | Medium | Implementation | Implementation
Dependency on vendor for maintenance and updates | Vendor & External Dependence | Governance | Vendor management; Governance | Greece | Public General Hospitals | ERP integration | Vendor lock-in | Low | Medium | Operations | Operations
Inadequate change management strategy | Stakeholder, Leadership & Cultural Issues | Governance | Change management; Governance | Greece | Public General Hospitals | ERP integration | Weak change plan | Low | Medium | Planning | Planning/Design
Limited patient involvement in EHR design and implementation | Stakeholder, Leadership & Cultural Issues | Patient Engagement | Patient Engagement; Governance | Finland | Public Hospital System | EHR implementation | Patient exclusion | Low | High | Planning/Design | Planning/Design
EHR focus primarily on administrative and clinician needs over patient needs | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Culture | Finland | Public Hospital System | EHR implementation | Clinician/admin bias | Low | High | Planning | Planning/Design
Lack of transparency for patients regarding data usage | Regulatory, Legal & Policy Risks | Security/Privacy | Privacy; Governance | Finland | Public Hospital System | EHR implementation | Opacity in data handling | Low | High | Operations | Operations
Technical interface not optimized for patient comprehension | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors | Finland | Public Hospital System | EHR implementation | Low health literacy support | Low | High | Design | Planning/Design
Insufficient channels for patient feedback in EHR development lifecycle | Stakeholder, Leadership & Cultural Issues | Patient Engagement | Governance; Patient Engagement | Finland | Public Hospital System | EHR implementation | Feedback gaps | Low | High | Planning/Operations | Operations
Risk of reinforcing unequal access to healthcare information for certain patient groups | Organisational Performance & Benefits Realisation | Patient Engagement | Equity; Accessibility | Finland | Public Hospital System | EHR implementation | Digital divide | Low | High | Operations | Operations
Poor alignment between policy-level patient engagement goals and technical EHR delivery | Regulatory, Legal & Policy Risks | Governance | Governance; Strategy | Finland | Public Hospital System | EHR implementation | Policy-practice gap | Low | High | Planning/Implementation | Planning/Design
Lack of formal project management frameworks in healthcare organisations | Project Management & Governance Failures | Governance | Governance; Strategy | USA | Mixed Healthcare Settings | Healthcare project management | No PM standardisation | High | High | Planning | Planning/Design
Poor stakeholder engagement throughout project lifecycle | Stakeholder, Leadership & Cultural Issues | Governance | Stakeholder management; Governance | USA | Mixed Healthcare Settings | Healthcare project management | Low stakeholder involvement | High | High | Planning/Implementation | Planning/Design
Insufficient training for project managers and team members | Human Resources, Training & User Support | Human Factors | Training; Human Factors | USA | Mixed Healthcare Settings | Healthcare project management | Skills gap | High | High | Deployment | Deployment
Ineffective communication between multidisciplinary teams | Stakeholder, Leadership & Cultural Issues | Governance | Communication; Governance | USA | Mixed Healthcare Settings | Healthcare project management | Miscommunication | High | High | Implementation/Operations | Implementation
Resistance to adopting structured project management methods | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Culture | USA | Mixed Healthcare Settings | Healthcare project management | Cultural resistance | High | High | Planning/Deployment | Deployment
Inadequate leadership support for project initiatives | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Leadership | USA | Mixed Healthcare Settings | Healthcare project management | Weak executive sponsorship | High | High | Planning | Planning/Design
Ambiguous project goals and unclear success metrics | Project Management & Governance Failures | Governance | Governance; Strategy | USA | Mixed Healthcare Settings | Healthcare project management | Unclear objectives | High | High | Planning | Planning/Design
Resource constraints including time, budget, and staffing | Financial & Resource Constraints | Financial | Financial; Workforce | USA | Mixed Healthcare Settings | Healthcare project management | Resource limitations | High | High | Planning/Implementation | Planning/Design
Lack of monitoring and evaluation mechanisms for project performance | Project Management & Governance Failures | Governance | Monitoring; Governance | USA | Mixed Healthcare Settings | Healthcare project management | No performance tracking | High | High | Operations | Operations
Failure to manage scope creep effectively | Project Management & Governance Failures | Governance | Project management; Governance | USA | Mixed Healthcare Settings | Healthcare project management | Scope creep | High | High | Implementation | Implementation
Overreliance on informal processes instead of documented procedures | Project Management & Governance Failures | Governance | Process; Governance | USA | Mixed Healthcare Settings | Healthcare project management | Informal approach | High | High | Planning/Operations | Operations
Lack of change management planning for transitions | Stakeholder, Leadership & Cultural Issues | Governance | Change management; Governance | USA | Mixed Healthcare Settings | Healthcare project management | No change plan | High | High | Planning/Deployment | Deployment
Poor data quality undermines the accuracy of analytics | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | USA | All Hospital Types | Healthcare business analytics | Inaccurate/incomplete datasets | High | High | Design/Implementation | Implementation
Lack of integration between analytics tools and operational systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | USA | All Hospital Types | Healthcare business analytics | Integration gaps | High | High | Design/Implementation | Implementation
Limited analytics skills among healthcare workforce | Human Resources, Training & User Support | Human Factors | Workforce; Training | USA | All Hospital Types | Healthcare business analytics | Skills gap | High | High | Planning/Operations | Operations
Resistance to adopting analytics-driven decision-making | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Culture | USA | All Hospital Types | Healthcare business analytics | Cultural resistance | High | High | Planning/Deployment | Deployment
Privacy and security concerns over patient data use in analytics | Security & Cyber Risks | Security/Privacy | Privacy; Security | USA | All Hospital Types | Healthcare business analytics | HIPAA/privacy compliance | High | High | Operations | Operations
Difficulty in translating analytics insights into clinical practice | Workflow & Process Misalignment | Governance | Governance; Implementation | USA | All Hospital Types | Healthcare business analytics | Insight-to-action gap | High | High | Operations | Operations
Lack of leadership support for analytics initiatives | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Leadership | USA | All Hospital Types | Healthcare business analytics | Weak executive sponsorship | High | High | Planning | Planning/Design
High costs of analytics infrastructure and maintenance | Financial & Resource Constraints | Financial | Financial; Infrastructure | USA | All Hospital Types | Healthcare business analytics | Cost burden | High | High | Planning/Operations | Operations
Insufficient real-time analytics capability | Technical System & Infrastructure Failures | Technical | Technical; Timeliness | USA | All Hospital Types | Healthcare business analytics | Delay in insights | High | High | Operations | Operations
Lack of standardized metrics and benchmarks for performance evaluation | Risk Framework & Analytical Weaknesses | Governance | Governance; Monitoring | USA | All Hospital Types | Healthcare business analytics | Metric inconsistency | High | High | Planning/Operations | Operations
Unauthorized access to patient records | Security & Cyber Risks | Security/Privacy | Security; Privacy | Australia | Networked Hospital System | EHR implementation | Access control gaps | Low | High | Operations | Operations
Inadequate authentication mechanisms (weak passwords, shared accounts) | Security & Cyber Risks | Security/Privacy | Security; Technical | Australia | Networked Hospital System | EHR implementation | Weak login protocols | Low | High | Design/Implementation | Implementation
Poor password management by staff | Human Resources, Training & User Support | Security/Privacy | Human Factors; Security | Australia | Networked Hospital System | EHR implementation | Password sharing, weak credentials | Low | High | Operations | Operations
Unencrypted data transmission across network | Security & Cyber Risks | Security/Privacy | Security; Technical | Australia | Networked Hospital System | EHR implementation | Interception risk | Low | High | Design/Implementation | Implementation
Data loss due to inadequate backup and recovery processes | Security & Cyber Risks | Data Quality | Data Quality; Technical | Australia | Networked Hospital System | EHR implementation | Backup failures | Low | High | Operations | Operations
Malware and virus attacks compromising system integrity | Security & Cyber Risks | Security/Privacy | Security; Technical | Australia | Networked Hospital System | EHR implementation | Malicious software | Low | High | Operations | Operations
Poor network security configuration (e.g., firewall misconfigurations) | Security & Cyber Risks | Security/Privacy | Security; Infrastructure | Australia | Networked Hospital System | EHR implementation | Firewall/config issues | Low | High | Implementation/Operations | Implementation
Lack of disaster recovery planning and testing | Project Management & Governance Failures | Governance | Governance; Risk management | Australia | Networked Hospital System | EHR implementation | No DRP or drills | Low | High | Planning/Operations | Operations
Limited user training on security and operational protocols | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Australia | Networked Hospital System | EHR implementation | Awareness gaps | Low | High | Deployment/Operations | Deployment
No intrusion detection or real-time monitoring system | Security & Cyber Risks | Security/Privacy | Monitoring; Security | Australia | Networked Hospital System | EHR implementation | No IDS | Low | High | Operations | Operations
Single points of failure causing potential system downtime | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Australia | Networked Hospital System | EHR implementation | SPOF risk | Low | High | Operations | Operations
Physical security weaknesses for servers and network equipment | Security & Cyber Risks | Security/Privacy | Physical Security; Infrastructure | Australia | Networked Hospital System | EHR implementation | Unauthorized physical access | Low | High | Operations | Operations
Lack of role-based access controls for different user types | Security & Cyber Risks | Security/Privacy | Governance; Security | Australia | Networked Hospital System | EHR implementation | Role privilege mismanagement | Low | High | Planning/Implementation | Planning/Design
Delay in applying software patches and updates | Project Management & Governance Failures | Governance | Technical; Governance | Australia | Networked Hospital System | EHR implementation | Patch management gaps | Low | High | Operations | Operations
Inadequate logging and audit trails for user activity | Project Management & Governance Failures | Governance | Monitoring; Governance | Australia | Networked Hospital System | EHR implementation | Accountability gaps | Low | High | Operations | Operations
Poorly defined procedures for incident response | Project Management & Governance Failures | Governance | Governance; Risk management | Australia | Networked Hospital System | EHR implementation | No IR plan | Low | High | Planning/Operations | Operations
Risk of insider misuse of EHR data | Security & Cyber Risks | Security/Privacy | Security; Governance | Australia | Networked Hospital System | EHR implementation | Insider threat | Low | High | Operations | Operations
Insufficient bandwidth causing performance degradation | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Australia | Networked Hospital System | EHR implementation | Network congestion | Low | High | Operations | Operations
Failure to comply with privacy regulations | Regulatory, Legal & Policy Risks | Ethical/Legal | Regulatory; Governance | Australia | Networked Hospital System | EHR implementation | Privacy law breach | Low | High | Planning/Operations | Operations
Lack of contingency for hardware failure | Technical System & Infrastructure Failures | Governance | Infrastructure; Risk management | Australia | Networked Hospital System | EHR implementation | No redundancy | Low | High | Planning/Operations | Operations
Poor data quality affecting analytics outcomes | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Global/International | All Hospital Types | Business analytics in healthcare | Inaccurate/incomplete datasets | High | High | Design/Implementation | Implementation
Limited interoperability between disparate data sources | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Global/International | All Hospital Types | Business analytics in healthcare | Integration gaps | High | High | Design/Implementation | Implementation
Lack of standardized data formats and coding systems | Technical System & Infrastructure Failures | Governance | Governance; Data Quality | Global/International | All Hospital Types | Business analytics in healthcare | Standardisation gap | High | High | Planning/Implementation | Planning/Design
Privacy and security risks from expanded data use | Security & Cyber Risks | Security/Privacy | Privacy; Security | Global/International | All Hospital Types | Business analytics in healthcare | HIPAA/GDPR compliance | High | High | Operations | Operations
Shortage of skilled analytics professionals in healthcare | Human Resources, Training & User Support | Human Factors | Workforce; Training | Global/International | All Hospital Types | Business analytics in healthcare | Skills gap | High | High | Planning/Operations | Operations
Resistance to adopting analytics in decision-making | Stakeholder, Leadership & Cultural Issues | Human Factors | Change management; Culture | Global/International | All Hospital Types | Business analytics in healthcare | Cultural resistance | High | High | Planning/Deployment | Deployment
Difficulty integrating predictive analytics into clinical workflows | Workflow & Process Misalignment | Technical | Workflow; Technical | Global/International | All Hospital Types | Business analytics in healthcare | Process misalignment | High | High | Design/Implementation | Implementation
Potential bias in AI/ML models leading to inequitable care | Risk Framework & Analytical Weaknesses | Ethical/Legal | Ethics; Clinical Safety | Global/International | All Hospital Types | Business analytics in healthcare | AI bias risk | High | High | Design/Operations | Operations
High implementation and maintenance costs for analytics platforms | Financial & Resource Constraints | Financial | Financial; Infrastructure | Global/International | All Hospital Types | Business analytics in healthcare | Cost burden | High | High | Planning/Operations | Operations
Limited real-time analytics capability | Technical System & Infrastructure Failures | Technical | Technical; Timeliness | Global/International | All Hospital Types | Business analytics in healthcare | Delay in insights | High | High | Operations | Operations
Fragmented governance structures for analytics projects | Project Management & Governance Failures | Governance | Governance; Strategy | Global/International | All Hospital Types | Business analytics in healthcare | Unclear accountability | High | High | Planning | Planning/Design
Poor data quality undermining dashboard accuracy | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Global/International | All Hospital Types | Dashboard implementation/evaluation | Inaccurate/incomplete data | High | High | Design/Implementation | Implementation
Lack of interoperability with other hospital IT systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Global/International | All Hospital Types | Dashboard implementation/evaluation | Integration gaps | High | High | Design/Implementation | Implementation
Overly complex visual design leading to user confusion | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors | Global/International | All Hospital Types | Dashboard implementation/evaluation | Cognitive overload | High | High | Design | Planning/Design
Insufficient alignment between dashboard metrics and clinical/operational goals | Workflow & Process Misalignment | Governance | Governance; Strategy | Global/International | All Hospital Types | Dashboard implementation/evaluation | Metric relevance gap | High | High | Planning | Planning/Design
Inadequate training for dashboard users | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Global/International | All Hospital Types | Dashboard implementation/evaluation | Skills gap | High | High | Deployment/Operations | Deployment
Limited stakeholder engagement during dashboard development | Stakeholder, Leadership & Cultural Issues | Governance | Governance; Stakeholder management | Global/International | All Hospital Types | Dashboard implementation/evaluation | Engagement gap | High | High | Planning/Design | Planning/Design
Inconsistent data refresh rates leading to outdated information | Technical System & Infrastructure Failures | Technical | Technical; Timeliness | Global/International | All Hospital Types | Dashboard implementation/evaluation | Lagging updates | High | High | Operations | Operations
Poor accessibility for users with disabilities | Workflow & Process Misalignment | Patient Engagement | Accessibility; Human Factors | Global/International | All Hospital Types | Dashboard implementation/evaluation | Non-inclusive design | High | High | Design | Planning/Design
Lack of standardized evaluation criteria for dashboard performance | Risk Framework & Analytical Weaknesses | Governance | Governance; Monitoring | Global/International | All Hospital Types | Dashboard implementation/evaluation | No evaluation framework | High | High | Planning/Operations | Operations
Security vulnerabilities in web-based dashboards | Security & Cyber Risks | Security/Privacy | Security; Technical | Global/International | All Hospital Types | Dashboard implementation/evaluation | Cybersecurity gaps | High | High | Operations | Operations
Data quality issues from inaccurate or missing sensor readings | Technical System & Infrastructure Failures | Data Quality | Data Quality; Technical | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Sensor errors | Medium | Medium | Operations | Operations
Connectivity interruptions affecting data transmission | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Network instability | Medium | Medium | Operations | Operations
Limited interoperability with hospital EHR and other systems | Technical System & Infrastructure Failures | Technical | Interoperability; Technical | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Integration gaps | Medium | Medium | Design/Implementation | Implementation
Security vulnerabilities in transmitting patient data | Security & Cyber Risks | Security/Privacy | Security; Privacy | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Data breach risk | Medium | Medium | Operations | Operations
Lack of real-time analytics due to processing delays | Technical System & Infrastructure Failures | Technical | Technical; Timeliness | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Delay in insights | Medium | Medium | Operations | Operations
Insufficient user training for healthcare staff managing remote monitoring | Human Resources, Training & User Support | Human Factors | Training; Human Factors | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Skills gap | Medium | Medium | Deployment/Operations | Deployment
Difficulty in visualizing and interpreting complex sensor data | Workflow & Process Misalignment | Workflow/Process | Usability; Human Factors | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Dashboard complexity | Medium | Medium | Design | Planning/Design
Dependence on stable power and internet infrastructure in remote areas | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Power/internet reliance | Medium | Medium | Operations | Operations
Limited scalability to handle large patient populations | Technical System & Infrastructure Failures | Technical | Infrastructure; Technical | Malaysia | Remote Monitoring Context | Remote healthcare monitoring system | Scalability limits | Medium | Medium | Planning/Operations | Operations